## Sheet1
Day | Person | Hours worked | Tasks Completeted | Hourly Rate | Compensation | Project Total
2026-04-06 | Jacob K | 1 | Downloaded NRI Metadata | 40 | 40 | 1063.5
2026-04-07 | Jacob L | 1 | Downloaded Metadata and SVI | 35 | 35
2026-04-07 | Jacob L | 2 | Wrote scope of work | 35 | 70
2026-04-08 | Eli S | 2 | Cleaned and organized data | 37 | 74 | Person | Hourly Rate
2026-04-09 | Jacob L | 1 | Handled Missing Values | 35 | 35 | Jacob L | 35
2026-04-09 | Eli S | 2 | Create Gantt Chart | 37 | 74 | Jacob K | 40
2026-04-10 | Jacob K | 1 | Joined Datasets | 40 | 40 | Eli S | 37
2026-04-11 | Eli S | 2 | Worked on reproducing NRI Methods | 37 | 74
2026-04-13 | Jacob K | 1 | Defined Flood risk | 40 | 40
2026-04-13 | Jacob L | 1 | Defined Wildfire risk | 35 | 35
2026-04-13 | Eli S | 2 | Analysis | 37 | 74
2026-04-13 | Jacob K | 1.5 | Edited Visuals | 40 | 60
2026-04-15 | Jacob L | 1.5 | Made tables and figures | 35 | 52.5
2026-04-16 | Eli S | 2 | Made Geopandas Map | 37 | 74
2026-04-18 | Jacob K | 2.5 | create annotated code document | 40 | 100
2026-04-18 | Eli S | 3 | Created written report | 37 | 111
2026-04-19 | Jacob L | 1 | Create github repository and upload files | 35 | 35
2026-04-20 | Jacob K | 1 | Create ReadMe for Github Repo | 40 | 40